## UITestSteps
TCID | TC Description | SID | Test Step Description | Execute | Result | P/F | Fail Description
TC001 | Create list (CL) | 1 | CL Button is clickable | P | P | Pass
TC001 | Create list (CL) | 2 | CL Button prompts user input | P | P | Pass
TC001 | Create list (CL) | 3 | CL Button prompt accepts valid input | P | O | Fail | Empty String is accepted
TC001 | Create list (CL) | 4 | Entered input is added as a list name | P | O | FAIL | CRASHES ON APOSTROPHE; OTHERWISE WORKS
TC001 | Create list (CL) | 5 | Input is added to SQL Table | P | P | Pass
TC001 | Create list (CL) | 6 | "Cancel" closes prompt | P | P | Pass
TC002 | Autosave List | 1 | List saves changes made to its name on UI | P | P | Pass
TC002 | Autosave List | 2 | List saves to lists table in DB | P | P | Pass
TC002 | Autosave List | 3 | List saves on Item Menu UI when adding items | P | P | Pass
TC002 | Autosave List | 4 | List saves in DB when adding items | P | O | Fail | Item does not persist when exiting to main menu
TC002 | Autosave List | 5 | List saves on UI when updating quantity | P | P | Pass
TC002 | Autosave List | 6 | List saves in DB when updating quantity | P | O | Fail | Quantity is not a persisting attribute
TC002 | Autosave List | 7 | List saves on UI when checking item | P | P | Pass
TC002 | Autosave List | 8 | List saves in DB when checking item | P | O | Fail | Checkmark is not a persisting attribute
TC003 | Long Press (LP) | 1 | LP opens up options for list | P | P | Pass
TC003 | Long Press (LP) | 2 | LP "Rename" applies said function | P | P | Pass
TC003 | Long Press (LP) | 3 | LP "Delete" applies said function | P | P | Pass
TC004 | Rename list | 1 | Opens up keyboard prompt for user input | P | P | Pass
TC004 | Rename list | 2 | Entered input accepted as valid input | P | P | Pass
TC004 | Rename list | 3 | Input overwrites current list's name in UI | P | P | Pass
TC004 | Rename list | 4 | List is renamed in DB | P | P | Pass
TC005 | Delete list | 1 | After tapping, prompts for user confirmation | O | O | Fail | Functionality not yet implemented
TC005 | Delete list | 2 | Removes list from UI | P | P | Pass
TC005 | Delete list | 3 | Removes list from DB | P | P | Pass
TC006 | Add item (AI) | 1 | AI Button is clickable | P | P | Pass
TC006 | Add item (AI) | 2 | AI Button prompts user to input a string | P | P | Pass
TC006 | Add item (AI) | 3 | Keyboard takes input and invokes search | P | P | Pass
TC006 | Add item | 2 | Search = Positive -> Adds item to list UI | P | P | Pass
TC006 | Add item | 3 | Added Item has checkbox on the left | P | P | Pass
TC006 | Add item | 4 | Added Item has quantity value starting at 1 | P | P | Pass
TC006 | Add item | 5 | Duplicate Items are not added | P | O | Fail | Adds duplicate items
TC006 | Add item | 6 | Search = Neg. -> Asks if input should be added to DB | P | P | Pass
TC006 | Add item | 7 | Search = Neg. -> Prompts for Item Type | P | P | Pass
TC006 | Add item | 8 | Search = Neg. -> Adds Item to DB and UI List | P | P | Pass
TC007 | Search Method | 1 | Checks for valid input (no numbers or special chars) | O | O | Fail | Adds all input into DB regardless of invalidity
TC007 | Search Method | 2 | Prompts toast if an exception occurs (violates above) | O | O | Fail | Functionality not yet implemented
TC007 | Search Method | 3 | Forces input to be all lowercase for simple DB search | O | O | Fail | Functionality not yet implemented
TC007 | Search Method | 4 | Compares to items in Items table to return true/false | P | P | Pass
TC008 | Check item | 1 | Checkbox is clickable | P | P | Pass
TC008 | Check item | 2 | Checking an item shows visual confirmation in UI | P | P | Pass
TC008 | Check item | 3 | Checking is represented in DB with boolean values | O | O | Fail | Checking does not persist
TC008 | Check item | 4 | Checked boxes can be unchecked by tapping | P | P | Pass
TC009 | Update Quantity | 1 | Only shows valid numbers to be updated to | P | P | Pass
TC009 | Update Quantity | 2 | Updating shows change in value on UI | P | P | Pass
TC009 | Update Quantity | 3 | Updating changes value in corresponding table in DB | O | O | Fail | Quantity does not persist
TC009 | Update Quantity | 4 | Updating to 0 deletes the item | P | O | Fail | Current Implementation can't update to 0
TC010 | Delete item (LP) | 1 | LP opens up delete option for item | O | O | Fail | Functionality not yet implemented
TC010 | Delete item (LP) | 2 | Pressing delete option removes item from UI | O | O | Fail | Functionality not yet implemented
TC010 | Delete item (LP) | 3 | Checkbox and Quantity are deleted with the item in UI | O | O | Fail | Functionality not yet implemented
TC010 | Delete item (LP) | 4 | Item is removed from corresponding table in DB | O | O | Fail | Functionality not yet implemented
TC011 | Group Type (GBT) | 1 | Adding an item groups it by type in alphabetical order | O | O | Fail | Functionality not yet implemented
TC012 | Group Type (GBT) | 2 | Grouped Items persist after exiting | O | O | Fail | Functionality not yet implemented